## Slide 1: Progress Report on proposed GUID on Information TECHNOLOGY Audit
A presentation by SAI India for 27th INTOSAI WGITA

## Slide 2: Introduction - background
New project taken due to FIPP directions
Revise ISSAI 5300 as GUID on Information Technology Audit as part of SDP 2.8 - Consolidating and aligning guidance on IT Audit
Project now titled - Guidelines on Information Technology Audit in support of Financial, Performance and Compliance Audits

## Slide 3: Introduction - background
Recommended numbering in 5100 - 5109 series (reserved for guidance on IT Audit)
Approved Project Duration:
  10.10.2017 to 30.09.2019 (24 months)
  in line with FIPP deadline
Members of Project Team
  Lead: India
  Members: Australia, Poland, Russia, USA

## Slide 4: Project Objectives
Draw upon existing Standards (ISACA), guidelines and frameworks (COBIT) and similar material related to IT audit
Align with ISSAI 100 and ISSAIs viz. ISSAI 200, 300 and 400
Consult material contained in GUID 5450 and other guidance
To be overarching, general principles GUID on IT Audit and provide basis for GUIDs on IT related specific subject matter
Require alignment with ongoing WGITA Project for revising ISSAI 5310 on IT Security Audit

## Slide 5: Rationale for revision
ISSAI 5300, with detailed sections on macro- and micro-level planning of IT Audits, gave an impression that IT Audit was distinct type of audit
‘Requirements’ portion made it appear like a Standard
While content of ISSAI 5300 would be preserved, update needed to define, elaborate, and harmonize how Information Technology (IT) Audits relate to and support Financial, Performance, and Compliance Audits

## Slide 6: Proposed Timelines and Progress Achieved
Stages | Due process milestones |  |  | 
Project Proposal | Start Date | End Date | Expected time in total | Comments
 | 10.10.2017 | 30.11.2017 | 50 Days | Project proposal and detailed outline approved
Exposure draft | 01.03.2018 | 31.07.2018 | 5 months | In progress
Exposure period | 01.11.2018 | 31.01.2019 | 90 Days | Yet to commence
Endorsement Version | 01.02.2019 | 30.04.2019 | 3 months | Yet to commence
Final pronouncement | 01.08.2019 | 30.09.2019 | 60 days | Yet to commence

## Slide 7: FIPP requirements on Project Proposal
Revised GUID will need to ensure alignment with ISSAIs 100, 200, 300 and 400
Need for more clarity on project scope with reference to IT audit being treated as specific subject matter and for proposing inclusion of high level principles of IT audit
GUID should make high level references to subjects like Information Security Audit and Cyber Security
STATUS:
  Detailed outline focusses on FIPP requirements

## Slide 8: Current Status
Following FIPP’s approval of detailed outline:
  Finalising Exposure Draft of GUID is in progress
  Detailed comments on proposed sections of GUID have been requested from all Team Members by April 30, 2018

## Slide 9: Proposal before WGITA
WGITA members are requested to take note of
  Progress Report
  Project Schedule
  Detailed Outline of GUID (circulated)
Suggested that the guidance may be renamed as
  Guidance on Auditing Information Systems

## Slide 10: Thanks…