## Slide 1: Documentation Requirements of an IT Audit including Audit Management System (Area: Audit Process)
A presentation by
SAIs AFROSAI-E, Bangladesh, China, Ecuador, Georgia, India, Indonesia, Iraq, Kuwait, and Mexico

## Slide 2: AGENDA
Project Synopsis (Project 5)
Project Plan 1 (Documentation Requirements of an IT Audit)
  Updated Project plan
  Deliverables
  Results
Project Plan 2 (Audit Management System)
  Deliverables
  Updated Project plan
  Preliminary survey results
  Following activities

## Slide 3: 1. Project Synopsis
Documentation Requirements of an IT Audit including Audit Management System (Area: Audit Process)
Introduction
At 24thWGITA meeting, it was discussed that WGITA in collaboration with IDI may consider developing AMS and it was decided to conduct a survey during 2015, 16 of 23 respondents were in favour of inclusion of AMS as a project, however, as many members have also shown interest for the project on: “Documentation Requirement for an IT audit”, Audit Management System may be included as part of this project 5, to achieve the resulted scope, two subprojects were defined:
Notes: The original Project 5 requirement was only the Documentations requirement of an IT audit, but in the 25wth WGITA was decide to include the Audit Management System in the scope of Project 5

## Slide 4: Project Synopsis
Subproject 1, Documentation requirements of an IT Audit
Taking in consideration the overall documentation requirements in an IT Audit would essentially flow from Level 3 ISSAIs viz~ ISSAIs 100, 200, 300 and 400, the approach of this subproject is to conduct a survey to identify specific adjustment to the documentation process in an IT Audit.
Subproject 2 Audit Management System (AMS)
For the development of a useful AMS for the different SAIS, it was proposed to initiate the project with the identification of a Generic Audit Process or part of the process that is common and produce value to the majority of SAIs, define this process in tree steps:
The first approach of a Generic Audit Process with functional requirements will be developed by members of project 5.
The Generic Audit Process will be enhanced with the feedback of members of the WGITA.
With the enhanced version, a survey will be conducted with all SAIs
With the result of the survey, a feasibility analysis for the AMS will be done, and if the AMS is feasible, a business case will be developed.
Notes: Two subproject was developed by Project 5 group, each project has its own scope and plan because there are no dependencies

## Slide 5: 2. Project Initiation Document
1. Documentation requirements of an IT Audit
Issues to be covered/Scope of the project
The survey will identify specific adjustments to the documentation process of an IT Audit in each of the following phases:
Planning
Execution
Reporting and Follow up
Termination
Archiving and disposal
The level of standardization of the documentation in terms of checklists, specimen letters, organization of working papers, and the retention and protection requirements of the documentation.
Deliverables
Guideline with the description of the specific adjustments in the documentation process of an IT audit in each of the following phases:
  Planning
  Execution
  Reporting and Follow up
  Termination
  Archiving and disposal
Notes: To develop Project 1 a survey was developed to identify the level of standardizations of the documentations
The first step in the survey was to ask to members of project 5, to Describe the documentations requirements (the level of standardization of the documentation in terms of checklists, specimen letters, organization of working papers, and the retention and protection requirements of the documentation) in an IT audit in each of the following activities of an audit process, mark the level of importance off the requirement, from 1 low to 5 high importance
Planning
Establish the terms of the audit
Obtain an understanding of the nature of the entity / programme to be audited
Develop an audit plan
Execution
Perform the planned procedures to obtain audit evidence
Evaluate audit evidence and draw conclusions
Reporting and follow-up
Prepare a report based on the conclusions reached
Follow up on reported matters as relevant
Termination
Closing the audit
Archiving and disposal
Archiving audit documentation
Disposal of audit documentation

## Slide 6: Updated Project Plan 1 Documentation requirements of an IT Audit
Notes: The project was planned to be developed in a 3 year period, there was a deviation reported in 2018, and the activities were rescheduled.
Due to the recommendation to not continue with the subproject, all the activities marked in blue were not necessary to develop.

## Slide 7: Documentation requirements of an IT Audit Deliverables
Survey applied to Project 5 members
Example of Mexican SAI survey
Survey adjustment (feedbacks from Project 5 members)
Results of the survey
  It was identified that there is no specific documentation requirements for an IT audit, to develop a guideline
  It was not required to conduct a survey to al SAIs
  It is recommended to finish the project
Notes: A Survey was sent to all Project 5 member SAIs (8 SAIs and AFROSAI representation) to identify the documentation requirements of an IT audit.
Besides the SAI of Mexico inputs, two SAIs (Ecuador and Kuwait) sent their responses.
With the analysis of the three SAI’s responses (Ecuador, Kuwait and Mexico) it was identified that all relevant documentation described in the activities developed during the Planning, Execution, Reporting and Follow Up and Termination phases of an IT audit was almost the same as any other type of audit.
The analysis of the survey reveals that there is no relevant specific documentation required for an IT audit.

## Slide 8: 3. Project Initiation Document
Audit Management System (AMS)
Issues to be covered/Scope of the project
In order to identify if there is a Generic Audit Process or part of the process that is common and produce value to the majority of SAIs:
A first approach of a Generic Audit Process with functional requirements will be developed by members of this project.
An enhanced version of the Generic Audit Process with functional requirements will be developed with the feedback of the members of the WGITA.
A survey will be conducted with all SAIs to identify if the result is Generic Audit Process or part of the process is common to the majority of SAIs and the level value that the functional requirements produce to each SAI.
With the result of the survey, a feasibility analysis for the AMS will be done with the process or part of the process that produce more value to the majority of SAIs.
It the AMS is feasible, a business case will be developed describing: objective, scope costs, resources, sponsors, schedules, risks, tasks and benefits, and also a project plan with development phases, resources allocation, INTOSAI and external participation, milestones, project leader.
Deliverables
Generic Audit Management Process
Feasibility analysis
Business Cases (if it is feasible)
Project plan (if the business case is approved)

## Slide 9: Updated Project Plan 2 Audit Management System
Notes: The project was planned to be developed in a 3 year period, there was a deviation reported in 2018, and the activities were rescheduled.

## Slide 10: Audit Management System Deliverables
Investigation of Generic Audit Process, with available public SAI web information, and results of technical surveys, main conclusions
  Many SAIs follow the INTOSAI General Process
  SAIs own subprocess and activities, difficult to standardize at these levels
  Particular SAI attributions (related to the country regulation)
  Common use of commercial software for word processing, project management, spreadsheets (e.g. Ms Office, acrobat)
  Customization of risk assessment and control evaluation methodologies
  Common implementations of BI and data analytics applications (e.g. click view, Tableau)
With the analysis of the conclusions, the Generic Audit Process should take in consideration:
  Define general functionalities that could be customized to particular sub process and activities of each SAI
  Integrate standards and methodologies (v.g. risk management and control evaluation)
  Integrate commercial software for word processing, project management, spreadsheets (e.g. Ms Office, acrobat)
  Integration with BI and data analytics applications
  Generic Audit Process (First approach)
Enhanced version of Generic Audit Process
  Feedback from WGITA members was consolidated, analyzed and applied to develop an enhanced version of the Generic Audit Process
  With the enhanced version of the Generic Audit Process, a survey was developed and was sent to all SAIs
Notes: A First approach to a Generic Audit Process was sent for comments to all Project 5 member SAIs (8 SAIs and AFROSAI representation).
Comments were received from the SAIs of Ecuador, Kuwait and AFROSAI representation.
The comments were analyzed, resulting in no substantial changes in the proposed Generic Audit Process.
39 SAI had sent the survey response
Palestine, Slovak Republic, Republic of Lativa ,Turkey, Luxembourg, Senegal, Peru, Chile, Jamaica, Costa Rica, Guatemala, South Africa, Bulgaria, Finland, Trinidad and Tobago, Republica Dominicana ,Gabon, Ecuado,r Egypt, Zambia, Republic of Azerbaijan, Spain, Macedonia, France, Algeria, Suriname, Lithuania Thailand, Kuwait, Belize, Estonia, Buthan, Puerto Rico, Fij,i Bahrian, Phillippines, Australia, Georgia, Mexico

## Slide 11: Preliminary Survey Results
Notes: 39 survey responses were analyzed the graph represent the number of responses of the choices of
N = Not applied / No value
D = Desired but not required
R = Required
M = Mandatory
for each of the 18 Process functionalities
The green color represent that a functionality is consider mandatory (dark green) o required (clear green)
The yellow color represent that a functionality is between required and desired (yellow) o desired (orange)

## Slide 12: Preliminary Survey Results
Notes: 39 survey responses were analyzed the graph represent the number of responses of the choices of
N = Not applied / No value
D = Desired but not required
R = Required
M = Mandatory
for each of the 6 General functionalities
The green color represent that a functionality is consider mandatory (dark green) o required (clear green)
The yellow color represent that a functionality is between required and desired (yellow) o desired (orange)

## Slide 13: Preliminary Survey Results
1. Access Control.
3. Log management.
6. Data backup and restoration.
6. Integration with specific audit plans.
7. Definition of audit processes and controls (for each audit).
13. Risk evaluation
14. Electronic management for summaries of audit observations, conclusions and recommendations
16. Integration of auditee responses and action plans
18. Complete audit quality control checklist.
2. Selection of risk assessment methodology.
3. Conduction/performance of risk assessment of the auditee universe.
10. Electronic file management.
11. Task management.
12. Cause and effect analysis.
17. Development of follow up plans.
4. Knowledge management.
5. Business intelligence and reporting.
Audit Process
Functionalities
General
Functionalities
Desired
Mandatory
Required
Notes: The analysis of the audit process functionalities identifies
6 mandatory
6 required
3 between required and desired
3 desired
The analysis of the general functionalities identifies
3 mandatory
1 between required and desired
2 desired
There was no functionality identified as not applied or not value

## Slide 14: Following activities
Obtain responses of the survey of All SAIs
Consolidate responses
Develop a feasibility study
Develop business case and project plan

## Slide 15
Thank You