## Slide 1
On the Development of the Cybersecurity and Data Protection Guideline
PROGRESS
30th Annual WGITA virtual meeting.
September 1st, 2021.

## Slide 2
Content
Work meetings.
2. Chapter assignment progress.
3. Project plan review.
4.External organization feedback.
5. Additional remarks.

## Slide 3
First meeting for the development of the Cybersecurity and Data Protection Guideline
December 8, 2020.

## Slide 4
Follow-up meeting for the development of the Cybersecurity and Data Protection Guideline
August 5, 2021.

## Slide 5
Chapter assignment progress

## Slide 6
Link to Answers provided to the Survey
https://forms.office.com/Pages/AnalysisPage.aspx?id=o5Yhb7yVT0qBFiVxl-Yyy4Xa7yqGPlZGvk3wXHb4yrxUNFkyTkdWSzdBQjFaQVI4RTBLMFVMOVhZUS4u&AnalyzerToken=ZBYyyiNGIEIABgirzbGehY3L3Xe2P3fb
Survey questions arrangement
  Chapter 1: Introduction. (Questions 1 - 8).
  Chapter 2: Guidance during audit phases. (Questions 9 - 17).
  Chapter 3: National Cybersecurity and data protection. (Questions18 – 24).
  Chapter 4: Cybersecurity and Data Protection by Sectors. (Questions 25 -30).
  Chapter 5 Cybersecurity implications in relevant and emerging technologies. (Questions 31 – 37).

## Slide 7
Work on the Development of Chapters is available for team members in the following link: https://asfgobmx-my.sharepoint.com/:f:/g/personal/wgita_asf_gob_mx/ElY7mxKpDMpFhsQzI89rargBjAwbhbCMTMDFn0xjG1-sUQ

## Slide 8
Index

## Slide 9
Chapter 1. Introduction.
Chapter | Brief content description | Lead | Member (s) | Progress Summary – Next Steps
1 Introduction | Data Protection and Data Privacy bared to cybersecurity (centered around confidentiality, integrity and availability), brief referral to relevant concepts, definitions, methodologies, standards and frameworks for a) referential purposes b) circumscribed to the audit guidance content of our document. Tools and technical references will be included. | USA and India | Kuwait , Argentina and Mexico | A draft outline has been prepared and shared with task members for review, feedback, additions, editions and comments. SAI USA has noted that some areas of the chapter may be impacted by the development of other chapters. To further develop these areas, we will be reaching out to the rest of the team members. SAI India, appointed along SAI USA as co-lead, specifically pertaining to develop the subject on data protection and data privacy bared to cybersecurity is developing the applicable content pertaining to the subject matter at hand. SAI Argentina has informed SAI Mexico that they will no longer be able to participate as team members in the development of the appointed assignment.

## Slide 10
Chapter 2. Guidance during audit phases.
Chapter | Brief content description | Lead | Member (s) | Progress Summary – Next Steps
2 Guidance during audit phases | Includes audit guidance, how to start audits on cybersecurity and data protection (planning, execution, reporting, follow up, termination, file and disposal). Tools and technical references will be included. | Australia | India and Japan | A draft outline is in progress. Once the draft is shared, SAI Mexico will reach out to the rest of the team members for review and feedback.

## Slide 11
Chapter 3. National Cybersecurity and data Protection.
Chapter | Brief content description | Lead | Member (s) | Progress Summary – Next Steps
3 National Cybersecurity and data protection | As part of the intent to provide SAIs with guidance (including relevant information such as the applicable framework when conducting such audit types), this section provides highlights on a) national and regional cybersecurity benchmark studies from global and regional organizations (APEC, ASEAN, LAS, OAS, PIF, SAARC, among others) and b) national cybersecurity considerations (UN, ENISA, NIST, ITU, among others) in terms of disaster recovery, infrastructure protection and open data, among others. Case studies will be included. Tools and technical references will be included. | Mexico | China and Peru | A draft outline has been prepared and shared with task members SAI China and SAI Peru, as well as with the rest of the team members for review, feedback, additions, editions and comments. Once comments are received from task members, an adjusted version will be available in the One Drive shared by team members.

## Slide 12
Chapter 4. Considerations of cybersecurity and data Protection by sectors.
Chapter | Brief content description | Lead | Member (s) | Progress Summary – Next Steps
4 Considerations of cybersecurity and data protection by sectors | Cybersecurity audits require SAIs to consider the different economic sectors governments are involved in. Some examples include cybersecurity and data protection in the financial, energy, health care, telecommunications and e-commerce sectors. Case studies will be included. Tools and technical references will be included. | USA | Bangladesh | A draft outline has been prepared and shared with task member SAI Bangladesh and SAI Mexico for review, feedback, additions, editions and comments. SAI Mexico will reach out to the rest of the task members for the same purpose.

## Slide 13
Chapter 5. Cybersecurity implications in relevant and emerging technologies.
Chapter | Brief content description | Lead | Member (s) | Progress Summary – Next Steps
5 Cybersecurity implications in relevant and emerging technologies | Some of the emerging technologies that will be touched upon include Government Resource Planning (GRP), Data Base Management System (DBMS), Blockchain, Big data and analytics and Internet of Things (IoT). Tools and technical references will be included. | Australia | Turkey | A draft outline is in progress. Once the draft is shared, SAI Mexico will reach out to the rest of the team members for review and feedback.

## Slide 14
Following steps for the Development of the Cybersecurity and Data Protection Guideline.
Chapter outlines will be compiled into one single document.
Such document will be submitted for team member and WGITA member feedback.
Development of the content of each of the chapters will begin.

## Slide 15
Project plan review

## Slide 16
External organization feedback
Given the specialty of the subject, feedback will be seeked from external organizations.
As of today, ISACA has offered to cooperate in the revision of the Guideline.
External organizations: academic institutions, government entities and overall standard developers.
New volunteers – recommendations are welcome.

## Slide 17
Additional remarks