## Slide 1: WGITA Project 2 update Audit of IT management – Governance, Outsourcing, Sustainability
SAI India

## Slide 2: Project 2 goals and the team
Provide advanced level guidance to actual conduct of audits covering
  IT Governance
  IT Outsourcing
  IT Sustainability
    Enhanced checklists and examples
    Enable audit teams to make meaningful recommendations
Audit Guidance doc on IT Management

## Slide 3: Project Work Update
Practice Guide -
Audit of IT management

## Slide 4: Chapters and Sections
Chapter/ Section | Content | Status update
1 | Audit of IT Governance | 
1A | Risks re: IT governance | 
1B | Audit matrix on IT Gov | 
1C | Audit finds n recommendations | 
2 | Audit of IT Outsourcing (incl cloud computing) | 
2A | Risks re: Outsourcing | 
2B | Audit matrix on IT outsourcing | 
2C | Audit finds n recommendations | 
3 | Audit of IT Sustainability | 
3A | Sustainability Risks re: IT practices | 
3B | Audit matrix on IT sustainability | SAI Ecuador, India
 |  | -
Draft mapped to new Handbook and COBIT 2019
Revised draft done –covers cloud computing and traditional outsourcing. Team review on
Section drafted. Team review on
IT Gov audit program-
Handbook matrix updated – Team review on
Section drafted. (WGITA, ITWG n SAI)- Team review on
First draft done and reviewed
Revised draft in progress
Revised draft done. Team review on

## Slide 5: Section B – Audit matrices

## Slide 6: Section C Audit finds, best practices and recommendations

## Slide 7: Chapter 2A IT Outsourcing- Cloud computing

## Slide 8: Chapter 3 – Audit of IT Sustainability

## Slide 9: Areas to address
Guidance Doc on Audit of IT Management

## Slide 10: Project tasks before circulation
Sec 1C - Audit examples and recommendations – sync with new Handbook
Sec 2A – needs harmonisation with Handbook chapter – covers cloud services and audit areas in much deeper detail
Sec 2C – needs sync with examples indicated in the Handbook
Sec 3C – audit examples – responses during circulation of Exposure draft to WGITA members
Resizing of the final exposure draft

## Slide 11: Steps ahead
WGITA project 2-
Guidance doc on Audit of It Management

## Slide 12: What next ?
Circulate Exposure Draft to WGITA member SAIs, other forums –Aug 2022
Gather response and make necessary changes –Nov 2022
Final endorsement draft Submission to WGITA chair –Dec 2022
Make the Guidance doc available on WGITA website for enabling related audit engagements.

## Slide 13: Thank You
Questions ?
This Photo by Unknown Author is licensed under CC BY-ND